Equality Action Plan 2022-2025 – Update Spring 2023

Please note - The actions and priorities contained in this plan are also reflected in the school’s current School Development Plan, Accessibility Action Plan and the School’s Self Evaluation.

Actions are colour coded in line with the School Development and Accessibility Action Plan – Blue / completed, Green / ongoing, Amber / Delayed but ongoing, Red / not started

|  | Priorities | Action | Time Scale | Leads | Resources | Cost | Criteria for success and outcomes for pupils |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | To improve pupil participation across the full range of learners. | Relaunch twice termly school council with particular regard to how non-verbal pupils with SLD and PMLD access this activity Review agendas and organisation Discuss appropriate inclusive activities for school council including preparation before the meeting, use of symbols, signing, Talking Mats. School Council has met Spring 23. Pupils also involved in the SEND Youth Voice consultation – A session has been held on Therapies. Further sessions are to follow. | January 2023 | Department Leaders | Staff INSET October 2022 – Total Communication Department meetings – Spring Term 23 | No cost No cost | Non-verbal SLD and PMLD learners are able to access and participate in half termly school council sessions |
| Review July 2023 Review July 2024 Review July 2025 |

|  | Priorities | Action | Time Scale | Lead | Resources | Cost | Criteria for success and outcomes for pupils |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | For pupils and families with English as an additional language to make good and outstanding progress | Developing EAL awareness on entry to school Clearly identify and record pupil and parent needs on first contact with school and during transition between classes and further provision Revisit current pupil records to check any missing records Training for all staff on supporting pupils with EAL. – planned for summer term training sessions Assess and track progress for these pupils – Information for pupils for subject leaders in Teachers’ folder. | Ongoing | Kathy Lewis Lisa Negus Caroline Horgan | Training for staff from English Subject Leader – Spring Term 2023 Ensure EAL is recorded on pupils’ Communication Passports. Autumn 22 – to be monitored Spring 23 Admin Team and Family Support Worker to agree clear transition for entry into school. Autumn 22 Admin team to check records for missing entries. Deputy Head to enable and support teachers to track EAL learners’ progress – Autumn 22 | No cost No cost Included in cost of Evidence for Learning analysis software | Pupils with English as an additional language make good and outstanding progress |
|  |  | Ensure all families who have English as an additional language have access to an interpreter service | Ongoing | Lisa Negus | Interpreting services |  | Families with EAL are able to access all school information and are able to support the learning of their child. |
| Review July 2023 Review July 2024 Review July 2025 |

|  | Priorities | Action | Time Scale | Lead | Resources | Cost | Criteria for success and outcomes for pupils and staff |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3 | To ensure that the curriculum and assemblies reflect the cultural, religious, ethnic, gender and sexual diversity of the school, community and country we live in. | Review assemblies & festivals to ensure a good range to match the cultural, religious and ethnic diversity of the school. Work with Department Leaders to develop a new programme of assemblies. – Collective Worship Policy reviewed Spring 23 | January 2023 | Effie Giagkoglou – RE Subject Leader | Staff meeting January 2023 – rescheduled for later in Spring term |  | Assemblies reflect the cultural diversity of the school and its community. |
|  |  | Review the curriculum and resources to ensure that positive representation of all groups is included: cultural, religious, ethnic, gender and sexual diversity. – Department Leaders and Subject Leaders have reviewed theme cycle Spring Term 23 School has been accepted onto Inclusive and Nurturing Schools Programme which will provide further CPD for staff on diversity and HR with support from a Consultant 2024 | April 2023 | LMT Subject Leaders | Staff training Staff meetings |  | The school curriculum supports all pupils to feel included and represented |
| Review July 2023 Review July 2024 Review July 2025 |

|  | Priorities | Action | Time Scale | Lead | Resources | Cost | Criteria for success and outcomes for pupils and staff |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4 | To ensure all policy and practice at St Giles complies with the Single Equalities Policy | To raise awareness of equality issues at governor meetings – review FGB Spring 23 | FGB December 2022 and ongoing | Equalities Governor Ken Morcombe Kathy Lewis Headteacher Caroline Horgan Deputy Head | ACAS Training on Equality, diversity and inclusion: the essentials – Headteacher, Deputy Head and School Business Manager Deputy Head and Lower School Department Leader to attend Tackling Racism, Sexism, LGBTQ-phobia and harassment: The Essential Guide for Transforming School Culture Governors meeting time | £345 £498 | All policy and practice at St Giles promotes equality for all pupils. No pupil is treated less favourably because of: • age • disability • gender reassignment • pregnancy and maternity • race • religion or belief • sex • sexual orientation |
|  |  | Review and revise the existing equalities policy. | December 2022 |  |  |  |  |
|  |  | As school policies are reviewed ensure they are aligned with the equalities policy | Ongoing |  |  |  |  |
|  |  | Review and update information and equalities statement in policy on the website | December 2022 |  |  |  |  |
|  |  | Governor monitoring to include equalities issues – two Governor visits to strengthen action plan Spring 23 | Ongoing |  |  |  |  |
| Review July 2023 Review July 2024 Review July 2025 |
| 5 | To ensure easy access to play areas for all children | Improve access play activities all pupils Further develop access for pupils to outdoor play at St Giles through purchase of appropriate equipment and further development of outdoor area – paths, surfaces – large play equipment in place – ongoing work required on paths and fencing. Continue developing staff support and equipment for appropriate play activities for St Giles learners. – classes are preparing cards / resources with appropriate play activities for pupils. Upper School Department Leader monitoring Spring 23 | Autumn 2022 | Fiona Bell – PE Subject Leader Lisa Negus – School Business Manager | Staff training PE subject leader observations Ongoing redevelopment of outdoor area including wheelchair accessible play equipment See also Physical and sensory Faculty Action Plan | £20,000 – £15, 000 paid from donation from Rotarians | All pupils enjoy outdoor play regardless of their physical and sensory needs. |
| Review July 2023 Review July 2024 Review July 2025 |

|  | Priorities | Action | Time Scale | Lead | Resources | Cost | Criteria for success and outcomes for staff |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 6 | Promote diversity for the staff team at St Giles Ensure discrimination does not occur, Advance equality of opportunity Foster good relations between those who share a protected characteristic and those who do not. | To foster good relations and raise awareness of diversity and equality during meetings, staff induction, on INSET days and in CPD programme for staff – INSET day Summer 23 is being planned to incorporate this. School is reviewing induction for staff and will use TES training programme for this. School has been accepted onto Inclusive and Nurturing Schools Programme which will provide further CPD for staff on diversity and HR with support from a Consultant 2024 Staff Voice focus on how the school environment can be welcoming to all staff – Spring / Summer 23 | Ongoing planning with Equalities Governor and LMT | Equalities Governor Ken Morcombe Kathy Lewis Headteacher Caroline Horgan Deputy Head LMT Subject Leaders | ACAS Training on Equality, diversity and inclusion: the essentials – Headteacher, Deputy Head and School Business Manager Deputy Head and Lower School Department Leader to attend Tackling Racism, Sexism, LGBTQ-phobia and harassment: The Essential Guide for Transforming School Culture Governors meeting time | £345 £498 | All policy and practice at St Giles promotes equality for all including staff with the following characteristics: age disability gender reassignment marriage or civil partnership (in employment only) pregnancy and maternity race religion or belief sex sexual orientation |
|  |  | To measure regularly levels of anxiety, happiness, worthwhileness, life satisfaction and job satisfaction for the staff team using established metrics with by using the Anna Freud Wellbeing Measurement. The results will be analysed on an ongoing basis, reported back to Governors and the staff team and used to inform policy and actions. Spring Term 23 – staff survey – this has now been completed. The results have been shared with LMT and Governors. It will be shared with the staff team Summer 23. | Ongoing – at least annual |  |  |  |  |
|  |  | Include question on equality in the interview questions for all staff - This is now part of the interview process, but will be reviewed to ensure question is effective. | December 2022 |  |  |  |  |
|  |  | Review and revise the existing equalities policy / action plan to reflect this priority– updates for action plan and Collective Worship policy proposed Spring 23 | Ongoing |  |  |  |  |
|  |  | As school policies are reviewed ensure they are aligned with this priority - updates for Collective Worship policy proposed Spring 23 | Ongoing |  |  |  |  |
|  |  | Review and update information and equalities statement in policy on the website | December 2022 |  |  |  |  |
|  |  | Governor monitoring to include information on this priority – two Governor visits to discuss and strengthen action plan Spring 23 | Ongoing |  |  |  |  |
| Review July 2023 Review July 2024 Review July 2025 |
| 5 | To ensure easy access to play areas for all children | Improve access play activities all pupils Further develop access for pupils to outdoor play at St Giles through purchase of appropriate equipment and further development of outdoor area – paths, surfaces – large play equipment in place – ongoing work required on paths and fencing. Continue developing staff support and equipment for appropriate play activities for St Giles learners. – classes are preparing cards / resources with appropriate play activities for pupils. Upper School Department Leader monitoring Spring 23 | Autumn 2022 | Fiona Bell – PE Subject Leader Lisa Negus – School Business Manager | Staff training PE subject leader observations Ongoing redevelopment of outdoor area including wheelchair accessible play equipment See also Physical and sensory Faculty Action Plan | £20,000 – £15, 000 paid from donation from Rotarians | All pupils enjoy outdoor play regardless of their physical and sensory needs. |
| Review July 2023 Review July 2024 Review July 2025 |